## Engagement 1 - Master Data
| Defect Leakage | 13.98% | [5 empty] | Budgeted Effort | 49385 | (hrs) |  | 1086470
| Labor Effort Variance % | 11.54% |  | 5699 |  |  |  | Actual Effort | 55084 | (hrs) |  | 1211848
| Labor Cost Variance | 125378
| Test Coverage | [6 empty] | Cost per hr | 22 | $
Grouped Functions | Client Test Cycle | Planned Test Cases | Executed Test Cases | Backlogged Test Cases | Passed | Failed | WIP/ No Run | Blocked (due to defect) | Marked N/A | Pass Rate % | Fail Rate % | No Run % | Count of Defects
All Batch Loads | Cycle1 | 500 | 500 | 0 | 492 | 8 | 0 | 0 | 0 | 98.4% | 1.6% | 0% | 18
Batch Negative | Cycle2 | 947 | 761 | 0 | 740 | 21 | 119 | 21 | 46 | 78.14% | 2.218% | 14.78% | 21
Int Intg | Cycle3 | 309 | 432 | 140 | 429 | 3 | 17 | 0 | 0 | 138.8% | 0.9709% | 5.502% | 3
CSR | Cycle4 | 447 | 446 | 17 | 437 | 9 | 0 | 18 | 0 | 97.76% | 2.013% | 4.027% | 9
Ext Integ | Cycle5 | 338 | 291 | 18 | 285 | 6 | 42 | 23 | 0 | 84.32% | 1.775% | 19.23% | 6
Website + Perf | Cycle6 | 220 | 264 | 65 | 259 | 5 | 21 | 0 | 0 | 117.7% | 2.273% | 9.545% | 5
Regression | Cycle7 | 254 | 250 | 21 | 209 | 41 | 0 | 0 | 0 | 82.28% | 16.14% | 0% | 41
Retests + Smoke | Cycle8 | 189 | 210 | 0 | 209 | 1 | 0 | 0 | 0 | 110.6% | 0.5291% | 0% | 1
Count of User Story / Change Requests. | Service provider Test Group | Planned Test Cases | Executed Test Cases | Backlogged Test Cases | Passed | Failed | WIP/ No Run | Blocked (due to defect) | Marked N/A | Pass Rate % | Fail Rate % | No Run % | Count of Defects
21 | Group1 (Itr1-5) | 120 | 105 | 0 | 73 | 32 | 15 | 0 | 0 | 60.83% | 26.67% | 12.5% | 32
43 | Group2 (Itr6-10) | 285 | 208 | 15 | 156 | 67 | 16 | 5 | 56 | 54.74% | 23.51% | 7.368% | 55
50 | Group3 (Itr11-15) | 911 | 741 | 21 | 632 | 130 | 115 | 0 | 55 | 69.37% | 14.27% | 12.62% | 123
14 | Group4 (Itr16-20) | 509 | 385 | 115 | 444 | 56 | 22 | 18 | 84 | 87.23% | 11% | 7.859% | 60
17 | Group5 (Itr21-25) | 304 | 299 | 40 | 286 | 19 | 3 | 2 | 0 | 94.08% | 6.25% | 1.645% | 19
18 | Group6 (Itr26-30) | 410 | 253 | 5 | 214 | 44 | 45 | 0 | 112 | 52.2% | 10.73% | 10.98% | 37
15 | Group7 (Itr31-35) | 885 | 765 | 45 | 699 | 111 | 46 | 24 | 50 | 78.98% | 12.54% | 7.91% | 53
36 | Group8 (Itr36-40) | 1001 | 895 | 70 | 790 | 175 | 78 | 5 | 23 | 78.92% | 17.48% | 8.292% | 131
15 | Group9 (Itr41-45) | 768 | 704 | 83 | 630 | 157 | 54 | 10 | 0 | 82.03% | 20.44% | 8.333% | 95
2 | Group10 (Itr46-50) | 205 | 205 | 64 | 220 | 51 | 0 | 0 | 0 | 107.3% | 24.88% | 0% | 35
231
| Service provider Test Group | Executed Test Cases | Regression Scope | Actual Regression Execution
9.091% | Group1 (Itr1-5) | 105 | 105 | 21 | 2.303%
18.61% | Group2 (Itr6-10) | 208 | 313 | 62.6 | 4.561%
21.65% | Group3 (Itr11-15) | 741 | 1054 | 210.8 | 16.25%
6.061% | Group4 (Itr16-20) | 385 | 1439 | 287.8 | 8.443% |  |  | Budgeted | Actuals
7.359% | Group5 (Itr21-25) | 299 | 1738 | 347.6 | 6.557% |  |  | 49385 | 55100 | 11.57%
7.792% | Group6 (Itr26-30) | 253 | 1991 | 398.2 | 5.548%
6.494% | Group7 (Itr31-35) | 765 | 2756 | 551.2 | 16.78% |  |  |  | 5715
15.58% | Group8 (Itr36-40) | 895 | 3651 | 730.2 | 19.63%
6.494% | Group9 (Itr41-45) | 704 | 4355 | 871 | 15.44%
0.8658% | Group10 (Itr46-50) | 205 | 4560 | 4560 | 4.496%
|  | 4560 | 21962 | 8040.4
|  |  | 26522 | 12600.4 |  | 0.52491
Planned/Budgeted Effort Across Teams
Count of User Storys | Service provider Test Group | Requirements | Design | Development | Testing | Deployment | Documentation | Project Management | Shared Service
19 | Group1 (Itr1-5) | 240.9091 | 204.5455 | 1638.6364 | 781.8182 | 163.1818 | 138.6364 | 414.5455 | 907.2727
42 | Group2 (Itr6-10) | 493.29 | 418.8312 | 3355.303 | 1600.8658 | 334.1342 | 283.8745 | 848.8312 | 1857.7489
46 | Group3 (Itr11-15) | 573.5931 | 487.013 | 3901.5152 | 1861.4719 | 388.5281 | 330.0866 | 987.013 | 2160.1732
17 | Group4 (Itr16-20) | 160.6061 | 136.3636 | 1092.4242 | 521.2121 | 108.7879 | 92.4242 | 276.3636 | 604.8485
15 | Group5 (Itr21-25) | 195.0216 | 165.5844 | 1326.5152 | 632.9004 | 132.0996 | 112.2294 | 335.5844 | 734.4589
17 | Group6 (Itr26-30) | 206.4935 | 175.3247 | 1404.5455 | 670.1299 | 139.8701 | 118.8312 | 355.3247 | 777.6623
9 | Group7 (Itr31-35) | 172.0779 | 146.1039 | 1170.4545 | 558.4416 | 116.5584 | 99.026 | 296.1039 | 648.0519
22 | Group8 (Itr36-40) | 412.987 | 350.6494 | 2809.0909 | 1340.2597 | 279.7403 | 237.6623 | 710.6494 | 1555.3247
3 | Group9 (Itr41-45) | 172.0779 | 146.1039 | 1170.4545 | 558.4416 | 116.5584 | 99.026 | 296.1039 | 648.0519
2 | Group10 (Itr46-50) | 22.9437 | 19.4805 | 156.0606 | 74.4589 | 15.5411 | 13.2035 | 39.4805 | 86.4069
| 49385 | 2650 | 2250 | 18025 | 8600 | 1795 | 1525 | 4560 | 9980
|  | 30.81% | 26.16% | 209.6% | 100% | 20.87% | 17.73% | 53.02% | 116%
Actual Effort Across Teams
Count of User Storys | Service provider Test Group | Requirements | Design | Development | Testing | Deployment | Documentation | Project Management | Shared Service
19 | Group1 (Itr1-5) | 262.2727 | 209.0909 | 1830.3636 | 1232.7273 | 209.0909 | 138.6364 | 361.8182 | 763.6364
42 | Group2 (Itr6-10) | 537.0346 | 428.1385 | 3747.8874 | 2524.1558 | 428.1385 | 283.8745 | 740.8658 | 1563.6364
46 | Group3 (Itr11-15) | 624.4589 | 497.8355 | 4358.0087 | 2935.0649 | 497.8355 | 330.0866 | 861.4719 | 1802
17 | Group4 (Itr16-20) | 174.8485 | 139.3939 | 1220.2424 | 821.8182 | 139.3939 | 92.4242 | 241.2121 | 509.0909
15 | Group5 (Itr21-25) | 212.316 | 169.2641 | 1481.7229 | 997.9221 | 169.2641 | 112.2294 | 292.9004 | 618.1818
17 | Group6 (Itr26-30) | 224.8052 | 179.2208 | 1568.8831 | 1056.6234 | 179.2208 | 118.8312 | 310.1299 | 654.5455
9 | Group7 (Itr31-35) | 187.3377 | 149.3506 | 1307.4026 | 880.5195 | 149.3506 | 99.026 | 258.4416 | 545.4545
22 | Group8 (Itr36-40) | 449.6104 | 358.4416 | 3137.7662 | 2113.2468 | 358.4416 | 237.6623 | 620.2597 | 1309.0909
3 | Group9 (Itr41-45) | 187.3377 | 149.3506 | 1307.4026 | 880.5195 | 149.3506 | 99.026 | 258.4416 | 545.4545
2 | Group10 (Itr46-50) | 24.9784 | 19.9134 | 174.3203 | 117.4026 | 19.9134 | 13.2035 | 34.4589 | 89
| 55084 | 2885 | 2300 | 20134 | 13560 | 2300 | 1525 | 3980 | 8400
Count of User Storys | Service provider Test Group | Requirements | Design | Development | Testing | Deployment | Documentation | Project Management | Shared Service
19 | Group1 (Itr1-5) | 21.3636 | 4.5455 | 191.7273 | 450.9091 | 45.9091 | 0 | -52.7273 | -143.6364
42 | Group2 (Itr6-10) | 43.7446 | 9.3074 | 392.5844 | 923.29 | 94.0043 | 0 | -107.9654 | -294.1126
46 | Group3 (Itr11-15) | 50.8658 | 10.8225 | 456.4935 | 1073.5931 | 109.3074 | 0 | -125.5411 | -358.1732
17 | Group4 (Itr16-20) | 14.2424 | 3.0303 | 127.8182 | 300.6061 | 30.6061 | 0 | -35.1515 | -95.7576
15 | Group5 (Itr21-25) | 17.2944 | 3.6797 | 155.2078 | 365.0216 | 37.1645 | 0 | -42.684 | -116.2771
17 | Group6 (Itr26-30) | 18.3117 | 3.8961 | 164.3377 | 386.4935 | 39.3506 | 0 | -45.1948 | -123.1169
9 | Group7 (Itr31-35) | 15.2597 | 3.2468 | 136.9481 | 322.0779 | 32.7922 | 0 | -37.6623 | -102.5974
22 | Group8 (Itr36-40) | 36.6234 | 7.7922 | 328.6753 | 772.987 | 78.7013 | 0 | -90.3896 | -246.2338
3 | Group9 (Itr41-45) | 15.2597 | 3.2468 | 136.9481 | 322.0779 | 32.7922 | 0 | -37.6623 | -102.5974
2 | Group10 (Itr46-50) | 2.0346 | 0.4329 | 18.2597 | 42.9437 | 4.3723 | 0 | -5.0216 | 2.5931
Count of User Storys | Service provider Test Group | Requirements | Design | Development | Testing | Deployment | Documentation | Project Management | Shared Service
19 | Group1 (Itr1-5) | 21 | 5 | 192 | 451 | 46 | 0 | -52 | -144
42 | Group2 (Itr6-10) | 44 | 9 | 393 | 923 | 94 | 0 | -108 | -294
46 | Group3 (Itr11-15) | 52 | 11 | 456 | 1074 | 109 | 0 | -126 | -358
17 | Group4 (Itr16-20) | 14 | 3 | 128 | 301 | 31 | 0 | -35 | -96
15 | Group5 (Itr21-25) | 17 | 4 | 155 | 365 | 37 | 0 | -43 | -116
17 | Group6 (Itr26-30) | 18 | 4 | 164 | 386 | 39 | 0 | -45 | -123
9 | Group7 (Itr31-35) | 15 | 3 | 137 | 322 | 33 | 0 | -38 | -103
22 | Group8 (Itr36-40) | 37 | 8 | 329 | 773 | 79 | 0 | -90 | -246
3 | Group9 (Itr41-45) | 15 | 3 | 137 | 322 | 33 | 0 | -38 | -103
2 | Group10 (Itr46-50) | 2 | 0 | 18 | 43 | 4 | 0 | -5 | 3
| Additional Effort | Requirements | Design | Development | Testing | Deployment | Documentation | Project Management | Shared Service
| Additional Effort (Hrs) | 235 | 50 | 2109 | 4960 | 505 | 0 | -580 | -1580 |  | 5699
| Additional Effort (%) | 8.868% | 2.222% | 11.7% | 57.67% | 28.13% | 0% | -12.72% | -15.83%
| Impact on LEV | 4.124% | 0.8773% | 37.01% | 87.03% | 8.861% | 0% | -10.18% | -27.72%

## Engagement 2 - Master Data
12.34
Service provider Test Group | Count of User Story / Change Requests. | Planned functional test cases | Executed functional test cases | Backlogged functional test cases | Passed | Failed | WIP/No Run | Pass Rate % | Fail Rate % | No Run Rate % | Blocked | Count of Defects | Planned Regression test cases | Actual Regression test cases
Rel-Sprint 1 | 61.7 | 308.5 | 308.4906 | 0 | 271.48 | 37 | 0 | 88% | 11.99% | 0% | 0 | 35 | 308 | 308
Rel-Sprint 2 | 74.04 | 493.6 | 493.5849 | 0 | 431.9 | 62 | 0 | 87.5% | 12.56% | 0% | 0 | 41 | 801.6 | 801.5849
Rel-Sprint 3 | 98.72 | 592.32 | 592.3019 | 0 | 518.28 | 74 | 0 | 87.5% | 12.49% | 0% | 0 | 42 | 1393.92 | 1393.8868
Rel-Sprint 4 | 37.02 | 123.4 | 123.3962 | 0 | 111.06 | 12 | 0 | 90% | 9.725% | 0% | 0 | 16 | 1517.32 | 1517.283
Rel-Sprint 5 | 24.68 | 370.2 | 370.1887 | 0 | 320.84 | 49 | 0 | 86.67% | 13.24% | 0% | 0 | 49 | 1887.52 | 1887.4717
Rel-Sprint 6 | 185.1 | 715.72 | 715.6981 | 0 | 617 | 99 | 0 | 86.21% | 13.83% | 0% | 0 | 43 | 2603.24 | 2603.1698
Rel-Sprint 7 | 86.38 | 456.58 | 456.566 | 0 | 394.88 | 62 | 0 | 86.49% | 13.58% | 0% | 0 | 71 | 3059.82 | 3059.7358
Rel-Sprint 8 | 61.7 | 518.28 | 518.2642 | 0 | 456.58 | 61 | 0 | 88.1% | 11.77% | 0% | 0 | 61 | 3578.1 | 3578
Rel-Sprint 9 | 24.68 | 24.68 | 24.6792 | 0 | 23 | 2 | 0 | 93.2% | 8.104% | 0% | 0 | 4 | 3602.78 | 3602.6792
Total | 654.02 | 3603.28 | 3603.1698 | 0 | 3145.02 | 458 | 0 | 87.28% | 12.71% |  | 0 | 362 | 18752.3 | 18751.8113
| Planned/Budgeted Effort Across Teams | [11 empty] | 22355.58
Service provider Test Group | Requirements | Design | Development | Testing (Automation) | Deployment | Documentation | Project Management | Shared Service
Rel-Sprint 1 | 174.0698 | 147.7951 | 1184.0029 | 444 | 117.9076 | 100.1722 | 299.5314 | 655.5533
Rel-Sprint 2 | 208.8837 | 177.3541 | 1420.8034 | 600 | 141.4892 | 120.2067 | 359.4376 | 786.664
Rel-Sprint 3 | 278.5116 | 236.4721 | 1894.4046 | 1140 | 188.6522 | 160.2756 | 479.2502 | 1048.8853
Rel-Sprint 4 | 104.4419 | 88.6771 | 710.4017 | 240 | 70.7446 | 60.1033 | 179.7188 | 393.332
Rel-Sprint 5 | 69.6279 | 59.118 | 473.6011 | 540 | 47.1631 | 40.0689 | 119.8125 | 262.2213
Rel-Sprint 6 | 522.2093 | 443.3853 | 3552.0086 | 1380 | 353.7229 | 300.5167 | 898.5941 | 1966.6599
Rel-Sprint 7 | 243.6977 | 206.9131 | 1657.604 | 600 | 165.0707 | 140.2411 | 419.3439 | 917.7746
Rel-Sprint 8 | 174.0698 | 147.7951 | 1184.0029 | 840 | 117.9076 | 100.1722 | 299.5314 | 655.5533
Rel-Sprint 9 | 69.6279 | 59.118 | 473.6011 | 204 | 47.1631 | 40.0689 | 119.8125 | 262.2213
| 1845.1395 | 1566.6279 | 12550.4302 | 5988 | 1249.8209 | 1061.8256 | 3175.0326 | 6948.8651 | 34385.7419 | 756486.3209
Actual Effort Across Teams
Sprints | Requirements | Design | Development | Testing (Automation) | Deployment | Documentation | Project Management | Shared Service
Rel-Sprint 1 | 169 | 142 | 1285 | 424 | 117.9076 | 100.1722 | 260 | 655.5533
Rel-Sprint 2 | 208.8837 | 165 | 1666 | 384 | 141.4892 | 120.2067 | 260 | 786.664
Rel-Sprint 3 | 226 | 231 | 1789 | 960 | 188.6522 | 160.2756 | 260 | 1048.8853
Rel-Sprint 4 | 102 | 90 | 722 | 220 | 70.7446 | 60.1033 | 280 | 393.332
Rel-Sprint 5 | 69 | 61 | 462 | 560 | 47.1631 | 40.0689 | 260 | 262.2213
Rel-Sprint 6 | 528 | 440 | 3552 | 1420 | 353.7229 | 300.5167 | 280 | 1966.6599
Rel-Sprint 7 | 241 | 208 | 1648 | 540 | 165.0707 | 140.2411 | 260 | 917.7746
Rel-Sprint 8 | 165 | 140 | 1200 | 884 | 117.9076 | 100.1722 | 320 | 655.5533
Rel-Sprint 9 | 84 | 59.118 | 502 | 182 | 47.1631 | 40.0689 | 320 | 262.2213
| 1792.8837 | 1536.118 | 12826 | 5574 | 1249.8209 | 1061.8256 | 2500 | 6948.8651 | 33489.5134 | 736769.2944 | 19717.0265
Sprints | Requirements | Design | Development | Testing (Automation) | Deployment | Documentation | Project Management | Shared Service
Rel-Sprint 1 | -5.0698 | -5.7951 | 100.9971 | -20 | 0 | 0 | -39.5314 | 0
Rel-Sprint 2 | 0 | -12.3541 | 245.1966 | -216 | 0 | 0 | -99.4376 | 0
Rel-Sprint 3 | -52.5116 | -5.4721 | -105.4046 | -180 | 0 | 0 | -219.2502 | 0
Rel-Sprint 4 | -2.4419 | 1.3229 | 11.5983 | -20 | 0 | 0 | 100.2812 | 0
Rel-Sprint 5 | -0.62791 | 1.882 | -11.6011 | 20 | 0 | 0 | 140.1875 | 0
Rel-Sprint 6 | 5.7907 | -3.3853 | -0.0085564 | 40 | 0 | 0 | -618.5941 | 0
Rel-Sprint 7 | -2.6977 | 1.0869 | -9.604 | -60 | 0 | 0 | -159.3439 | 0
Rel-Sprint 8 | -9.0698 | -7.7951 | 15.9971 | 44 | 0 | 0 | 20.4686 | 0
Rel-Sprint 9 | 14.3721 | 0 | 28.3989 | -22 | 0 | 0 | 200.1875 | 0
| Additional Effort | Requirements | Design | Development | Testing | Deployment | Documentation | Project Management | Shared Service
| Additional Effort (Hrs) | -52.2558 | -30.5099 | 275.5698 | -414 | 0 | 0 | -675.0326 | 0 | -896.2285 | -2.606%
| Additional Effort (%) | -2.832% | -1.947% | 2.196% | -6.914% | 0% | 0% | -21.26% | 0%
| Impact on LEV | 5.831% | 3.404% | -30.75% | 46.19% | 0% | 0% | 75.32% | 0%
Client defects
| Sprint | Count of Defects
| Rel-Sprint 1 | 2
| Rel-Sprint 2 | 3
| Rel-Sprint 3 | 0
| Rel-Sprint 4 | 4
| Rel-Sprint 5 | 0
| Rel-Sprint 6 | 2
| Rel-Sprint 7 | 4
| Rel-Sprint 8 | 1
| Rel-Sprint 9 | 3
|  | 19 | 4.987%